EdgeASIC v4.8

32-Week Implementation Plan and Demo Strategy

Primary-Target Host-Assisted INT8 CNN / YOLOv8n Compute-Layer Accelerator

Two-person FYP execution plan with weekly RTL, verification, software, demo and evidence gates

Figure 1. 32-week phase roadmap for baseline, primary-target extensions, host-assisted demo and final defense.

Scope rule This plan treats Conv2D, Tensor Table, descriptor ring, graph scheduler, split, concat, upsample, SPPF/maxpool, LUT-SiLU, C2f sequencing, detect-head convolution and raw tensor export as primary targets. Decode, confidence filtering and NMS remain host-side software components in the primary demo unless a separate hardware postprocessing block is explicitly implemented and verified.

# Document Control

| Field | Value |
| --- | --- |
| Document | EdgeASIC v4.8 32-Week Implementation Plan and Demo Strategy |
| Project identity | Host-assisted INT8 Conv/GEMM accelerator with YOLOv8n compute-layer primary targets |
| Team size | Two people: Person A (datapath/math) and Person B (control/memory/software/verification infrastructure) |
| Planning duration | 32 weeks |
| Primary demo | CPU-only baseline vs CPU + EdgeASIC IP acceleration, with separate kernel and end-to-end timing |
| Document status | Planning and execution control document; not proof of RTL implementation or FPGA timing |

# Static Table of Contents

1. Executive Implementation Strategy

2. Primary Target Scope

3. Team Organization and Work Ownership

4. Phase Overview and Milestone Gates

5. Detailed Week-by-Week Plan

6. Verification and Evidence Strategy

7. Host-Assisted Demo Strategy

8. Performance Evaluation Plan

9. Risk Register and Recovery Rules

10. Repository and Deliverable Structure

11. Final Defense Package and Claim Discipline

Appendix A. Weekly test ID map

Appendix B. Weekly review template

# 1. Executive Implementation Strategy

The project is planned as a host-assisted accelerator rather than a standalone image-to-box processor. The hardware IP accelerates supported INT8 tensor compute and tensor movement tasks. The host software performs image preprocessing, quantization, descriptor generation, data transfer, unsupported software control tasks, final decode, NMS and drawing.

The plan is intentionally baseline-first. Weeks 1-16 establish a reliable, verifiable N=8 INT8 Conv/GEMM engine with CSR control, DMA abstraction, local SRAM/BRAM buffering, SDDU alignment, K-tile accumulation, requantization, residual ADD and partial-tile support. Weeks 17-32 add the promoted primary targets needed for a YOLOv8n-style compute-layer demonstration.

Performance message for presentation The project must report two metrics separately: (1) compute-kernel speedup, using CSR performance counters around Conv/GEMM or operator compute, and (2) end-to-end host-assisted time, including preprocessing, quantization, transfer, IP compute, transfer back and host postprocessing. This prevents overclaiming if transfer overhead dominates.

# 2. Primary Target Scope

| Target | Description | Status in this plan |
| --- | --- | --- |
| Baseline INT8 Conv/GEMM | N=8, 8x8 PE array, INT8 activations/weights, INT32 accumulation, SDDU, requantization | Must pass by Week 13 |
| Host-assisted execution | Host preprocessing, quantization, tiling, descriptors, data movement, decode/NMS and display | Primary demo model |
| Partial tiles | Lane masks and invalid-lane suppression for dimensions not divisible by 8 | Primary support target |
| Residual ADD | Residual SRAM plus 9-bit signed saturating add | Primary support target |
| Conv2D window generator | 1x1, 3x3, stride and padding address generation | Primary target |
| Tensor Table | Stores tensor base, shape, stride, scale and producer/consumer metadata | Primary target |
| Descriptor ring | Multi-layer descriptor queue | Primary target |
| Graph scheduler | In-order layer scheduling and dependency gating | Primary target |
| Tensor movement | Split, concat and nearest upsample | Primary target |
| YOLOv8n compute primitives | C2f decomposition, maxpool/SPPF, LUT-SiLU, detect-head convolution, raw tensor export | Primary target |
| Post-processing boundary | Decode, confidence filtering and NMS remain host software in this plan | Primary software target, not IP RTL |

## 2.1 Explicit Non-Goals Unless Separately Proven

No claim of full autonomous YOLOv8n hardware execution unless the complete model graph is implemented and verified end-to-end on the IP.

No claim of hardware decode or hardware NMS in this plan; decode and NMS are primary host-side software components.

No measured FPS, FPGA timing closure, DDR production integration or synthesis-success claim unless the actual tools and hardware evidence exist.

No N=16 physical implementation or sparsity-acceleration claim in this 32-week plan unless added as a separately verified extension.

# 3. Team Organization and Work Ownership

The original two-person split is kept, but verification ownership is rebalanced. Person B owns the shared verification environment, scoreboard, regression runner and host scripts. Each designer writes directed tests and assertions for the RTL blocks they implement. This avoids making Person B the bottleneck for every test case.

| Subsystem / activity | Primary owner | Secondary owner | Notes |
| --- | --- | --- | --- |
| System packages/types | A+B | Joint | Widths, enums, metadata structures and interface conventions must be frozen together. |
| CSR, descriptor manager, dispatcher | B | A reviews | B implements control plane; A confirms datapath fields and start/done/error contract. |
| Host software contract | B | A reviews | B owns driver interface and data movement scripts; A validates tensor math assumptions. |
| PE, systolic array, SDDU | A | B tests integration | A owns compute RTL and directed tests for timing and signed arithmetic. |
| Accumulation, requantization, activation | A | B scoreboard | A owns math path; B integrates scoreboard and CSR-visible errors. |
| DMA, SRAM/BRAM, BSC, packing FIFO | B | A reviews datapath timing | B owns memory movement; A validates lane order and tile consumption timing. |
| Partial tile and residual ADD | A+B | Joint | A owns datapath mask/add; B owns residual prefetch and bank ownership. |
| Conv2D window generator | A | B descriptors/tests | A owns address/window datapath; B extends descriptor and golden model harness. |
| Tensor Table, descriptor ring, graph scheduler | B | A co-designs ready/done | B owns scheduler implementation; A provides engine availability and tensor-consume signals. |
| Split, concat, upsample | B | A validates data order | B owns address generation/memory movement; A checks tensor order against datapath requirements. |
| Maxpool, SPPF, LUT-SiLU, detect-head conv | A | B test harness | A owns operator datapaths; B creates descriptors and model comparison flow. |
| Verification environment | B | A writes block tests | B owns regression/scoreboard; each designer writes tests for their own RTL. |
| Final presentation/demo | A+B | Joint | A explains datapath; B explains control, software contract, verification and metrics. |

## 3.1 Weekly Operating Procedure

Day 1: planning meeting, confirm weekly gate, split tasks and define evidence required.

Days 2-4: implementation and local unit tests. Every committed RTL block must have at least one directed test or clear TODO status.

Day 5: peer review. Person A reviews control/memory changes; Person B reviews datapath changes and tests.

Day 6: integration/regression run, waveform capture for timing-sensitive changes.

Day 7: bug fixes, documentation update and weekly gate decision. Do not start the next major phase until the gate is closed or explicitly waived with risk logged.

# 4. Phase Overview and Milestone Gates

Figure 2. CPU-only vs CPU + EdgeASIC IP demo model used for final performance comparison.

| Phase | Weeks | Focus | Exit gate |
| --- | --- | --- | --- |
| P0 | Week 1 | Scope freeze and project setup | Finalize primary targets, repo structure, coding rules, tensor layout contract and demo strategy. |
| P1 | Weeks 2-6 | Baseline foundations | Packages, CSR, descriptors, BSC, DMA, SRAMs, PE array and SDDU. |
| P2 | Weeks 7-13 | Baseline compute and integration | Accumulation, requantization, activation, memory routing, top-level FSMs, counters, errors and regression. |
| P3 | Weeks 14-16 | Current extensions | Partial tile masking, residual SRAM/ADD and baseline feature freeze. |
| P4 | Weeks 17-20 | Conv2D primary targets | Conv2D model, 1x1 Conv, 3x3 Conv, stride/padding and Conv2D regression. |
| P5 | Weeks 21-24 | Tensor scheduling and movement | Tensor Table, descriptor ring, graph scheduler, split/concat and raw tensor movement. |
| P6 | Weeks 25-28 | YOLOv8n compute primitives | Upsample, C2f sequencing, maxpool/SPPF, LUT-SiLU, detect-head convolution and raw tensor format. |
| P7 | Weeks 29-30 | Host-assisted demo and performance | CPU-only vs CPU+IP pipeline, timing breakdown, kernel speedup and system overhead reporting. |
| P8 | Weeks 31-32 | Final defense package | Documentation, waveforms, regression reports, slides, demo scripts and limitation statements. |

## 4.1 Mandatory Milestones

| Milestone | Target week | Required evidence |
| --- | --- | --- |
| M1 Scope and repo freeze | Week 1 | Module list, tensor layout contract, host/IP contract and primary target matrix approved. |
| M2 Control plane smoke | Week 3 | CSR, descriptor and dispatcher tests pass. |
| M3 Memory safety | Week 4 | BSC legal/illegal transitions and DMA 4KB local rejection pass. |
| M4 Compute core unit pass | Week 6 | PE array and SDDU data/metadata timing tests pass. |
| M5 Accumulation correctness | Week 7 | All four K_TILE_FIRST/K_TILE_LAST cases pass. |
| M6 Baseline output path | Week 9 | DMA router, output SRAM and packing FIFO tests pass. |
| M7 First end-to-end tile | Week 11 | At least one full Conv/GEMM tile matches Python golden model. |
| M8 Baseline regression | Week 13 | 20+ current-use tests and assertions pass. |
| M9 Current extensions freeze | Week 16 | Partial tile and residual tests pass or are explicitly disabled with status. |
| M10 Conv2D gate | Week 20 | 1x1 and selected 3x3/stride/padding tests pass. |
| M11 Tensor scheduling gate | Week 24 | Tensor Table, descriptor ring, graph scheduler, split/concat basics pass. |
| M12 YOLO operator gate | Week 28 | Implemented operator targets have passing TC IDs; raw tensor format is host-readable. |
| M13 Demo metrics | Week 30 | CPU-only vs CPU+IP logs, kernel timing and end-to-end overhead reported separately. |
| M14 Defense package | Week 32 | Repository, documents, waveforms, scripts, slides and limitation statements frozen. |

# 5. Detailed Week-by-Week Plan

The table below is the controlling implementation plan. Each week contains design tasks, verification tasks, deliverables and an exit gate. If the gate fails, the team records the slip in the issue tracker and either fixes the issue before continuing or explicitly limits the affected feature's final claim.

## 5.1 Weeks 1-8

| Week | Focus | Person A - datapath / math | Person B - control / memory / software | Deliverables | Verification / evidence | Exit gate |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Scope freeze and infrastructure | Review v4.8 architecture; freeze primary target list; define compute/dataflow assumptions; prepare PE/SDDU/accumulator test vector plan. | Create repo, naming convention, coding rules, testbench folder, CI/regression scripts; freeze tensor layout and host/IP contract. | Scope matrix, repository skeleton, interface naming standard, memory layout contract, demo boundary statement. | Review checklist proving no block is ambiguous before RTL begins. | Architecture and implementation scope frozen. |
| 2 | Packages, types, CSR skeleton and golden model | Define INT8/INT16/INT32/INT33/INT57 datapath types; define pipe_meta_t; define lane mask and valid rules. | Define enums, CSR register skeleton, status bits, W1C behavior; start Python INT8 GEMM golden model and tensor memory image format. | config_pkg, types_pkg, CSR skeleton, Python GEMM model, tensor packing script v0. | TC-BOOT-001 package compile; TC-CSR-001 reset values; Python model sanity tests. | Packages compile and CSR reset is visible. |
| 3 | Descriptor manager and operator dispatcher | Confirm descriptor fields needed by datapath engines; define start/done/error interface for compute engines. | Implement active/inactive descriptor manager, descriptor commit, operator dispatcher, unsupported op/activation latching. | descriptor_manager, operator_dispatcher, CSR error latches, descriptor unit testbench. | TC-CSR-002 W1C; TC-DESC-001 commit while idle; TC-DESC-002 reject unsafe commit; TC-ERR-001 unsupported OP; TC-ERR-002 unsupported ACT. | Only legal OP_TYPEs start engines; errors are sticky. |
| 4 | SRAM/BRAM, BSC and DMA rejection | Define activation/weight/bias/output/accumulator read/write timing needs; provide lane order expectations. | Implement SRAM wrappers, Bank State Controller, DMA abstraction, 4KB boundary detector, local dma_done+dma_error behavior. | activation/weight/bias/output SRAM wrappers, BSC, DMA abstraction, boundary error path. | TC-BSC-001 legal transitions; TC-BSC-002 illegal consume blocked; TC-DMA-001 4KB local rejection; TC-DMA-002 no deadlock timeout. | Local memory and DMA safety layer works. |
| 5 | PE and 8x8 systolic array | Implement signed PE, registered act_out, weight-stationary hold, 8x8 array; produce waveforms. | Build PE/array unit tests and connect with Python expected values; prepare debug memory images. | pe_mac, systolic_array_8x8, signed arithmetic testbench, act_out waveform evidence. | TC-PE-001 signed multiply; TC-PE-002 accumulation; TC-PE-003 registered act_out; TC-ARR-001 8x8 smoke test. | Array produces correct partial sums. |
| 6 | SDDU and metadata alignment | Implement SDDU delay[i]=N-1-i; carry data and pipe_meta_t together; handle valid bubbles/stalls. | Write SDDU timing assertions and metadata alignment tests; regression hook for waveforms. | sddu, lane-delay test, metadata alignment test, stall/bubble test. | TC-SDDU-001 delay direction; TC-SDDU-002 metadata alignment; SVA-SDDU-001 lane delay; SVA-META-001 metadata valid alignment. | Deskewed outputs and metadata are aligned. |
| 7 | Accumulation engine and K-tile behavior | Implement bias add once, four FIRST/LAST cases, external INT32 accumulation-buffer RMW, final drain gating. | Write accumulator scoreboard and RMW hazard tests; connect acc buffer model. | accum_engine, accum_buffer, K_TILE_FIRST/LAST path, final-drain rules. | TC-ACC-001 FIRST=1 LAST=1; TC-ACC-002 FIRST=1 LAST=0; TC-ACC-003 FIRST=0 LAST=0; TC-ACC-004 FIRST=0 LAST=1; SVA-ACC-001 no output before LAST. | Multi-K accumulation matches golden model. |
| 8 | Requantization and activation | Implement INT33->INT57 scaling, signed arithmetic shift, INT8 saturation, ACT_NONE and ACT_RELU. | Add quantization edge-case generator and activation-mode tests; verify unsupported LUT-SiLU behavior until RTL block is implemented later. | requant_pipeline, activation_unit, signed shift and saturation tests. | TC-REQ-001 signed shift; TC-REQ-002 saturation +127/-128; TC-ACT-001 ReLU; TC-ACT-002 passthrough; TC-ACT-ERR-001 LUT-SiLU unsupported before primary block enabled. | Quantized INT8 output matches golden model. |

## 5.2 Weeks 9-16

| Week | Focus | Person A - datapath / math | Person B - control / memory / software | Deliverables | Verification / evidence | Exit gate |
| --- | --- | --- | --- | --- | --- | --- |
| 9 | DMA read router, output SRAM and packing FIFO | Define output tile write order and 8-byte chunk expectations; debug datapath-output order. | Implement DMA read router, byte lane mapping, output SRAM write path, packing FIFO, backpressure handling. | dma_read_router, output_sram, packing_fifo, byte ordering tests. | TC-DMA-003 512-bit beat mapping; TC-FIFO-001 pack 8B to 64B; TC-FIFO-002 backpressure; TC-MEM-001 output ordering. | Memory movement can feed and drain the compute path. |
| 10 | Top-level baseline integration start | Connect PE->SDDU->accumulator->requant->activation->output path; debug timing slips. | Connect CSR->descriptor->dispatcher->FSMs->BSC->DMA; implement prefetch/compute/writeback FSM shells. | edgeasic_top baseline v0, prefetch_fsm, compute_fsm, writeback_fsm, first integration simulation. | TC-E2E-001 one-tile smoke; timeout guards; waveform review at every boundary. | One simple tile can start, compute and finish, even if bugs remain. |
| 11 | Baseline end-to-end debug | Fix internal datapath mismatches; compare internal accumulators and final outputs to golden model. | Improve memory preload, scoreboard, automated output compare and regression script. | End-to-end single K tile, multi-K tile and negative-value tests. | TC-E2E-002 single K tile; TC-E2E-003 multi-K tile; TC-E2E-004 negative tensors; scoreboard pass/fail log. | At least five baseline E2E tests pass. |
| 12 | Shape errors, sticky errors and performance counters | Expose compute_active, mac_active, stall and output_valid signals to counter block. | Implement shape validation, sticky errors, IRQ error, CSR-readable counters and PERF_CLEAR. | shape validator, performance counter block, error/IRQ integration. | TC-SHAPE-001 invalid M/K; TC-SHAPE-002 stride/padding illegal for baseline; TC-PERF-001 counters increment; TC-PERF-002 PERF_CLEAR; TC-ERR-003 error recovery. | Errors and performance counters are software visible. |
| 13 | Baseline regression hardening | Clean datapath code, run randomized small shapes, fix edge cases. | Run regression, add assertions, collect waveform and log evidence; prepare baseline freeze notes. | 20+ randomized baseline tests, assertion report, baseline regression report. | REG-CUR-001 full baseline suite; SVA coverage review; golden-model compare across cases. | Baseline N=8 Conv/GEMM is frozen enough for primary extensions. |
| 14 | Partial tile masking | Implement lane-valid mask for M/N edges; suppress invalid MACs, metadata and output writes. | Generate partial-tile tensors and checker; add descriptor flag behavior and shape tests. | partial_tile_mask logic integrated into compute/output paths. | TC-PTILE-001 M partial; TC-PTILE-002 N partial; TC-PTILE-003 M and N partial together; TC-PTILE-004 no invalid output writes. | Non-multiple-of-8 dimensions are correct. |
| 15 | Residual SRAM and residual ADD | Implement 9-bit signed residual ADD after activation, INT8 saturation, residual disabled passthrough. | Implement residual prefetch from INPUT1_BASE, residual SRAM ownership in BSC and residual shape checks. | residual_sram, elementwise_unit, residual BSC path. | TC-RES-001 residual disabled bit-exact baseline; TC-RES-002 residual add; TC-RES-003 +127/-128 saturation; TC-RES-004 residual bank ownership. | Residual path works and does not disturb baseline. |
| 16 | Baseline plus extension freeze | Fix partial/residual bugs; ensure all primary extension hooks are non-invasive. | Run full regression; update issue tracker and evidence package; checkpoint readiness for Conv2D phase. | Phase 1-3 regression report, known limitations list, mid-project demo package. | REG-CUR-002 baseline+partial+residual suite; checkpoint review. | Baseline and current extensions are stable. |

## 5.3 Weeks 17-24

| Week | Focus | Person A - datapath / math | Person B - control / memory / software | Deliverables | Verification / evidence | Exit gate |
| --- | --- | --- | --- | --- | --- | --- |
| 17 | Conv2D model and window generator specification | Design Conv2D window generator datapath for 1x1/3x3/stride/padding; write microarchitecture notes. | Extend descriptor fields for kernel, stride, padding; extend Python golden model for Conv2D/NHWC tiling. | Conv2D spec, Python Conv2D golden model, descriptor update, test-vector generator. | TC-CONV2D-SW-001 Python 1x1; TC-CONV2D-SW-002 Python 3x3; TC-CONV2D-SW-003 padding/stride; model verified before RTL integration. | Software model and descriptor contract are ready. |
| 18 | 1x1 Conv hardware path | Map 1x1 Conv to existing GEMM core; validate channel/output layout and quant path. | Generate descriptors and memory images for 1x1 Conv; add regression cases. | 1x1 Conv mode, descriptor support and tests. | TC-CONV1X1-001 single output channel tile; TC-CONV1X1-002 multi-channel tile; TC-CONV1X1-003 partial channel tile. | 1x1 Conv matches Python model. |
| 19 | 3x3 Conv window generator | Implement 3x3 window extraction and feed sequencing into systolic/GEMM core; handle zero padding for fixed case. | Build memory images and tests for 3x3 fixed stride/pad; validate byte ordering and row padding. | conv2d_window_generator v1, 3x3 fixed-case RTL tests. | TC-CONV3X3-001 fixed stride 1 same padding; TC-CONV3X3-002 valid padding; TC-CONV3X3-003 window order check. | Small fixed-case 3x3 Conv passes. |
| 20 | Stride/padding generalization and Conv2D gate | Extend window generator for descriptor-driven stride and padding; debug array utilization issues. | Run full Conv2D regression; decide whether general or fixed profiles are defense-ready. | Conv2D primary target regression report and gate review. | TC-CONV2D-004 stride 2; TC-CONV2D-005 padding boundaries; REG-CONV2D-001 1x1+3x3 suite. | Conv2D phase gate passed or downgraded with evidence. |
| 21 | Tensor Table implementation | Define datapath requirements for tensor shape/stride/scale consumption. | Implement Tensor Table storage, CSR/descriptor access, base/shape/stride/scale fields and baseline bypass compatibility. | tensor_table, tensor metadata tests, integration with DMA routing. | TC-TT-001 write/read entry; TC-TT-002 tensor base/shape decode; TC-TT-003 baseline descriptor direct mode still works. | Tensor metadata can be used by primary scheduling path. |
| 22 | Descriptor ring | Define engine-ready/done response timing for multi-descriptor execution. | Implement descriptor ring storage, fetch/commit sequence, ring empty/full handling and error propagation. | descriptor_ring, ring status counters, multi-descriptor tests. | TC-RING-001 push/pop descriptor; TC-RING-002 ring full; TC-RING-003 ring empty; TC-RING-004 descriptor error stops chain. | Multiple descriptors can be queued safely. |
| 23 | Graph scheduler | Expose per-engine ready/done/consume signals; co-design tensor dependency handshake. | Implement in-order graph scheduler, tensor dependency checks, layer completion update and dispatch rules. | graph_scheduler, layer done tracking, two-layer and three-layer chain tests. | TC-GRAPH-001 two-layer chain; TC-GRAPH-002 three-layer chain; TC-GRAPH-003 dependency not ready stalls; TC-GRAPH-004 error recovery. | Basic graph sequencing is functional. |
| 24 | Split and concat tensor movement | Validate output tensor format required by split/concat; debug channel ordering. | Implement split and concat address/control engines using Tensor Table metadata; add DMA/memory movement tests. | split_engine, concat_engine, tensor movement tests. | TC-SPLIT-001 channel split; TC-CONCAT-001 channel concat; TC-MOVE-001 no data corruption; TC-MOVE-002 partial channels. | Split/concat primary movement ops work. |

## 5.4 Weeks 25-32

| Week | Focus | Person A - datapath / math | Person B - control / memory / software | Deliverables | Verification / evidence | Exit gate |
| --- | --- | --- | --- | --- | --- | --- |
| 25 | Upsample and C2f sequencing | Support nearest-neighbor upsample datapath if implemented as address-repeat path; define C2f primitive order. | Implement upsample address generation; create C2f descriptor sequence using conv, split, residual and concat primitives. | upsample_engine, C2f sequencer documentation and small RTL/driver chain if stable. | TC-UP-001 2x nearest upsample; TC-C2F-001 small C2f-like chain; TC-C2F-002 tensor shape propagation. | Upsample and basic C2f chain are represented in runnable flow. |
| 26 | Maxpool and SPPF | Implement maxpool compare-tree datapath and repeated pooling flow for SPPF-like primitive. | Add descriptors, tests and Tensor Table updates for maxpool/SPPF output tensors. | maxpool_unit, SPPF sequencing path, pooling tests. | TC-POOL-001 2x2 maxpool; TC-POOL-002 5x5 or selected SPPF pool; TC-SPPF-001 repeated maxpool chain; TC-SPPF-002 concat compatibility. | Maxpool/SPPF target passes selected tests. |
| 27 | LUT-SiLU activation | Implement LUT-SiLU INT8 approximation or LUT-based activation mode; define interpolation/rounding policy. | Add LUT loading/configuration path or fixed ROM; create Python approximation model and error metrics. | lut_silu_unit, LUT contents, activation tests and error report. | TC-SILU-001 LUT correctness; TC-SILU-002 monotonic/edge values; TC-SILU-003 error bound vs Python model; TC-ACT-003 mode routing. | LUT-SiLU is no longer just unsupported; it has verified primary-target behavior. |
| 28 | Detect-head convolution and raw tensor output | Map detect-head conv to Conv/GEMM/Conv2D path; define raw detection tensor output layout. | Create detect-head descriptors, raw tensor export metadata and host-readable tensor dump format. | detect-head conv small synthetic test, raw tensor format spec, export flow. | TC-DETECT-001 detect-head-like conv; TC-RAW-001 tensor shape/layout; TC-RAW-002 byte-exact export; TC-HOST-001 host can parse raw tensor. | Raw detection tensor target is demonstrable. |
| 29 | Host software integration and demo path | Support debugging of output tensors and selected layer comparison; collect cycle counts from hardware counters. | Implement host driver scripts: preprocess, quantize, tile, write descriptors, run CPU-only baseline, run CPU+IP path, export raw tensors, run host decode/NMS. | Python/C++ host demo scripts, CPU-only vs CPU+IP run flow, logging format. | TC-HOST-002 descriptor write/read; TC-HOST-003 CPU vs IP tensor compare; TC-HOST-004 decode/NMS compatibility; DEMO-001 end-to-end script dry run. | Demo can run in controlled scripted form. |
| 30 | Performance evaluation and full system regression | Analyze IP compute utilization, stalls, array active cycles and bottlenecks; fix late datapath bugs. | Run system regression; collect kernel time, transfer time, host time and full pipeline time. | Performance evaluation report, kernel speedup chart, system overhead breakdown, regression log. | REG-SYS-001 all implemented targets; PERF-001 kernel speedup; PERF-002 full-system overhead; PERF-003 counters sanity. | Performance claims are evidence-backed and separated correctly. |
| 31 | Final documentation and evidence package | Prepare datapath diagrams, waveforms and module explanations; verify no current-vs-primary confusion remains. | Prepare verification report, test matrix, logs, host demo screenshots, no-go claims and limitation slide. | Final report chapters, waveform appendix, test evidence table, issue tracker closure. | DOC-001 claim/evidence mapping; DOC-002 no-go claim audit; QA review of diagrams and code references. | Documentation supports exactly what was implemented. |
| 32 | Final demo rehearsal and defense delivery | Rehearse datapath explanation, arithmetic correctness, bottleneck explanation and limitations. | Rehearse software flow, verification story, demo scripts, timing breakdown and examiner Q&A. | Defense package, final demo video/live demo, backup screenshots, final archive. | DEMO-002 live or recorded demo; DEF-001 Q&A checklist; REL-001 final repository/package freeze. | FYP package is ready for submission and defense. |

# 6. Verification and Evidence Strategy

Verification is not a final phase; it is attached to every implementation week. The plan uses directed SystemVerilog tests, assertions, Python golden models, host-driver checks, integration regression and waveform evidence. UVM is not required, but the testbench must still have a scoreboard, timeout protection and repeatable test vectors.

## 6.1 Test Ownership Rule

The designer of a block writes the first directed tests for that block.

Person B owns shared regression infrastructure and scoreboard integration, not every individual test case.

Every primary-target feature must have a TC-ID before RTL is integrated into the main branch.

A feature without a passing TC-ID cannot be claimed as implemented in the final report.

Timing-sensitive features require waveform screenshots or VCD/FSDB evidence, especially PE act_out, SDDU, accumulation RMW, BSC ownership, DMA routing and graph scheduling.

## 6.2 Verification Coverage by Phase

| Coverage group | Required coverage | Target weeks |
| --- | --- | --- |
| Baseline compute | PE signed arithmetic, registered act_out, 8x8 array timing, SDDU delay, metadata alignment | Weeks 5-6 |
| Accumulation and quant | K_TILE_FIRST/LAST cases, RMW hazard, final-subtile drain, signed shift, saturation, ReLU/passthrough | Weeks 7-8 |
| Memory movement | BSC legal/illegal transitions, DMA 4KB local rejection, byte ordering, packing FIFO backpressure | Weeks 4 and 9 |
| Control plane | CSR reset/W1C, descriptor commit, unsupported OP/ACT, shape errors, IRQ, performance counters | Weeks 2-3 and 12 |
| Current extensions | Partial tile masking, residual SRAM, residual ADD, disabled-feature regression | Weeks 14-16 |
| Conv2D primary targets | 1x1, 3x3, stride, padding, window order, NHWC layout | Weeks 17-20 |
| Graph and tensor movement | Tensor Table, descriptor ring, graph scheduler, split, concat, upsample | Weeks 21-25 |
| YOLOv8n primitives | C2f chain, maxpool, SPPF, LUT-SiLU, detect-head conv, raw tensor export | Weeks 25-28 |
| Demo/system | CPU-only vs CPU+IP compare, host decode/NMS compatibility, kernel timing, full-system overhead | Weeks 29-30 |

# 7. Host-Assisted Demo Strategy

The final demo must prove both correctness and acceleration value without overclaiming full autonomous YOLOv8n hardware. The CPU-only path acts as a reference. The CPU+IP path uses the host to prepare INT8 tensors and descriptors, then offloads supported operators to the IP. Host software reconstructs outputs, performs decode/NMS and draws boxes or compares tensors.

| Demo component | CPU-only path | CPU + IP path | Metric |
| --- | --- | --- | --- |
| Preprocessing | CPU/Python | CPU/Python | Same preprocessing time or separately reported. |
| Quantization | May be folded into CPU reference | Host converts to INT8 and packs tensors | Quantization time reported separately. |
| Conv/GEMM kernel | CPU implementation or framework | EdgeASIC IP | Kernel speedup from CPU time vs CSR compute cycles. |
| Primary operators | CPU reference | Implemented IP engines where available | Output match against Python golden model. |
| Transfers | None | Host-to-IP and IP-to-host transfer time | System overhead, not hidden. |
| Decode/NMS | CPU/Python | CPU/Python | Kept outside IP speedup claim. |
| Final output | Boxes or tensor outputs | Boxes or tensor outputs | Correctness comparison and visual demo. |

# 8. Performance Evaluation Plan

Report baseline analytical peak: 64 MAC/cycle for the 8x8 array; if a 200 MHz target is used, label it as a target until measured.

Report kernel-level metrics using CSR counters: total cycles, compute cycles, DMA wait cycles, stall cycles, writeback cycles and MAC-active cycles.

Report system-level metrics separately: preprocess time, quantization time, transfer-to-IP time, IP compute time, transfer-back time, host decode/NMS time and total time.

Do not compare unfairly against optimized laptop frameworks without clearly naming the baseline. Include at least one controlled CPU INT8 kernel for a fair same-operation comparison.

If CPU+IP full-system time is slower due to transfers, state that the prototype proves functional offload and kernel acceleration; production speedup requires higher bandwidth integration and more on-device graph execution.

| Metric | How to measure | Used for claim |
| --- | --- | --- |
| Kernel compute cycles | CSR performance counters around IP compute | Compute acceleration claim |
| Array utilization | MAC-active cycles / compute cycles | Datapath efficiency |
| DMA wait cycles | CSR DMA wait counter | Memory bottleneck analysis |
| CPU kernel time | Python/C++ timer around same INT8 operation | Kernel speedup denominator |
| Transfer time | Host timer around data movement | Full-system overhead |
| End-to-end time | Timer from preprocessed input or image input to final output | System demo claim only |
| Numerical correctness | Max absolute difference, pass/fail exactness for INT8 where expected | Correctness evidence |

# 9. Risk Register and Recovery Rules

| ID | Risk | Severity | Probability | Impact | Mitigation / recovery |
| --- | --- | --- | --- | --- | --- |
| R1 | Person B overload | Critical | High | Control, memory and verification are too concentrated on one person. | Both designers write block tests; joint integration weeks; avoid adding untested RTL without TC-ID. |
| R2 | Baseline slips past Week 13 | High | Medium | Primary targets cannot start safely if baseline is unstable. | Use Week 11 as integration buffer; protect baseline regression; no Conv2D until baseline passes. |
| R3 | K_TILE_FIRST/LAST bug | Critical | Medium | Bias or partial accumulation errors silently corrupt all outputs. | Four-case directed tests before random tests; SVA for no final output before LAST. |
| R4 | DMA byte ordering mismatch | High | Medium | Software/IP tensor layout mismatch creates wrong results that look like math bugs. | Freeze byte mapping in Week 2; run 00..3F beat pattern test before integration. |
| R5 | Conv2D window generator complexity | High | High | 3x3 stride/padding can consume more time than expected. | Start with fixed profile; verify Python model first; keep 1x1 Conv working even if generalization slips. |
| R6 | Graph scheduler instability | Critical | Medium | Multi-layer automatic execution can deadlock or corrupt tensor dependencies. | In-order only; no dynamic graph; small 2/3-layer chains before full sequences. |
| R7 | Operator target overload | High | High | Split, concat, upsample, SPPF, SiLU and detect head each need tests. | Each operator requires TC-ID before RTL; mark unsupported in demo if TC does not pass. |
| R8 | End-to-end speedup not visible | Medium | High | Host transfer overhead may hide kernel acceleration. | Report kernel speedup and system overhead separately; use counters for compute-only metric. |
| R9 | Overclaiming YOLOv8n | High | Medium | Examiner may reject if full YOLO hardware is implied. | Use wording: YOLOv8n compute-layer primary targets; decode/NMS host-side unless proven otherwise. |
| R10 | Insufficient evidence | High | Medium | RTL may work but cannot be defended without logs/waveforms. | Weekly evidence checklist; save waveform screenshots and regression logs starting Week 5. |

## 9.1 Feature Claim Recovery Rule

Because many primary targets are aggressive for a two-person team, the plan uses a claim-control rule: a scheduled target remains a primary target, but it can only be claimed as implemented if its RTL, host interface and verification tests pass. If it does not pass, the final report must list it as attempted, partially complete, or disabled with a clear issue ID. This protects the FYP from overclaiming while preserving the ambitious primary-target roadmap.

# 10. Repository and Deliverable Structure

| Directory | Contents |
| --- | --- |
| rtl/pkg | config_pkg.sv, types_pkg.sv, op/act/ew enums, pipe_meta_t, descriptor structs |
| rtl/control | csr_block, descriptor_manager, descriptor_ring, graph_scheduler, operator_dispatcher, FSMs, error/IRQ logic |
| rtl/memory | SRAM wrappers, BSC, DMA abstraction, read router, packing FIFO, Tensor Table |
| rtl/datapath | PE, systolic array, SDDU, accumulator, requant, activation, residual, mask |
| rtl/operators | Conv2D window generator, split, concat, upsample, maxpool, SPPF, LUT-SiLU, detect-head mapping |
| tb/unit | Block-level directed testbenches |
| tb/integration | Top-level E2E and multi-layer chain tests |
| tb/golden | Python golden models for GEMM, Conv2D, quantization, activation, tensor movement and host postprocess |
| host | Python/C++ scripts for preprocessing, quantization, tiling, descriptors, CPU-only baseline and CPU+IP run |
| docs/evidence | Waveforms, test logs, performance tables, screenshots and issue tracker |

## 10.1 Weekly Evidence Package

RTL files changed during the week.

Testbench files and Python golden-model changes.

Regression log showing pass/fail status.

Waveform screenshot for timing-sensitive blocks.

Short weekly note: what passed, what failed, what is blocked, what changes next week.

Updated issue tracker entries for unresolved bugs.

# 11. Final Defense Package and Claim Discipline

| Claim type | Allowed wording |
| --- | --- |
| Safe final claim | Implemented/verified modules with passing tests; host-assisted CPU+IP demo; kernel and system metrics reported separately. |
| Conditional claim | YOLOv8n compute-layer flow only for operators that pass TC-FUT/primary-target tests. |
| No-go claim | Full autonomous YOLOv8n hardware execution, hardware decode/NMS, measured real-time FPS, FPGA timing closure, production DDR integration unless actually proven. |

## 11.1 Recommended Final Title

Design and Verification of a Host-Assisted INT8 Edge Inference Accelerator for YOLOv8n Compute-Layer Prototyping

## 11.2 Recommended Final Claim

We implemented and verified a host-assisted INT8 edge inference accelerator that offloads Conv/GEMM and selected YOLOv8n compute-layer primary targets to a 64-PE systolic hardware IP. The host software handles preprocessing, quantization, descriptor generation, tensor transfers, CPU-only reference execution, final decode/NMS and output display. Kernel-level acceleration and full-system overhead are reported separately.

Mandatory non-claim disclaimer No autonomous full YOLOv8n hardware execution, hardware decode/NMS, measured real-time FPS, FPGA timing closure or production DDR integration is claimed unless the final evidence package includes passing implementation and measurement proof.

# Appendix A - Weekly Test ID Map

| Week | Focus | Key tests / evidence |
| --- | --- | --- |
| 1 | Scope freeze and infrastructure | Review checklist proving no block is ambiguous before RTL begins. |
| 2 | Packages, types, CSR skeleton and golden model | TC-BOOT-001 package compile; TC-CSR-001 reset values; Python model sanity tests. |
| 3 | Descriptor manager and operator dispatcher | TC-CSR-002 W1C; TC-DESC-001 commit while idle; TC-DESC-002 reject unsafe commit; TC-ERR-001 unsupported OP; TC-ERR-002 unsupported ACT. |
| 4 | SRAM/BRAM, BSC and DMA rejection | TC-BSC-001 legal transitions; TC-BSC-002 illegal consume blocked; TC-DMA-001 4KB local rejection; TC-DMA-002 no deadlock timeout. |
| 5 | PE and 8x8 systolic array | TC-PE-001 signed multiply; TC-PE-002 accumulation; TC-PE-003 registered act_out; TC-ARR-001 8x8 smoke test. |
| 6 | SDDU and metadata alignment | TC-SDDU-001 delay direction; TC-SDDU-002 metadata alignment; SVA-SDDU-001 lane delay; SVA-META-001 metadata valid alignment. |
| 7 | Accumulation engine and K-tile behavior | TC-ACC-001 FIRST=1 LAST=1; TC-ACC-002 FIRST=1 LAST=0; TC-ACC-003 FIRST=0 LAST=0; TC-ACC-004 FIRST=0 LAST=1; SVA-ACC-001 no output before LAST. |
| 8 | Requantization and activation | TC-REQ-001 signed shift; TC-REQ-002 saturation +127/-128; TC-ACT-001 ReLU; TC-ACT-002 passthrough; TC-ACT-ERR-001 LUT-SiLU unsupported before primary block enabled. |
| 9 | DMA read router, output SRAM and packing FIFO | TC-DMA-003 512-bit beat mapping; TC-FIFO-001 pack 8B to 64B; TC-FIFO-002 backpressure; TC-MEM-001 output ordering. |
| 10 | Top-level baseline integration start | TC-E2E-001 one-tile smoke; timeout guards; waveform review at every boundary. |

| Week | Focus | Key tests / evidence |
| --- | --- | --- |
| 11 | Baseline end-to-end debug | TC-E2E-002 single K tile; TC-E2E-003 multi-K tile; TC-E2E-004 negative tensors; scoreboard pass/fail log. |
| 12 | Shape errors, sticky errors and performance counters | TC-SHAPE-001 invalid M/K; TC-SHAPE-002 stride/padding illegal for baseline; TC-PERF-001 counters increment; TC-PERF-002 PERF_CLEAR; TC-ERR-003 error recovery. |
| 13 | Baseline regression hardening | REG-CUR-001 full baseline suite; SVA coverage review; golden-model compare across cases. |
| 14 | Partial tile masking | TC-PTILE-001 M partial; TC-PTILE-002 N partial; TC-PTILE-003 M and N partial together; TC-PTILE-004 no invalid output writes. |
| 15 | Residual SRAM and residual ADD | TC-RES-001 residual disabled bit-exact baseline; TC-RES-002 residual add; TC-RES-003 +127/-128 saturation; TC-RES-004 residual bank ownership. |
| 16 | Baseline plus extension freeze | REG-CUR-002 baseline+partial+residual suite; checkpoint review. |
| 17 | Conv2D model and window generator specification | TC-CONV2D-SW-001 Python 1x1; TC-CONV2D-SW-002 Python 3x3; TC-CONV2D-SW-003 padding/stride; model verified before RTL integration. |
| 18 | 1x1 Conv hardware path | TC-CONV1X1-001 single output channel tile; TC-CONV1X1-002 multi-channel tile; TC-CONV1X1-003 partial channel tile. |
| 19 | 3x3 Conv window generator | TC-CONV3X3-001 fixed stride 1 same padding; TC-CONV3X3-002 valid padding; TC-CONV3X3-003 window order check. |
| 20 | Stride/padding generalization and Conv2D gate | TC-CONV2D-004 stride 2; TC-CONV2D-005 padding boundaries; REG-CONV2D-001 1x1+3x3 suite. |

| Week | Focus | Key tests / evidence |
| --- | --- | --- |
| 21 | Tensor Table implementation | TC-TT-001 write/read entry; TC-TT-002 tensor base/shape decode; TC-TT-003 baseline descriptor direct mode still works. |
| 22 | Descriptor ring | TC-RING-001 push/pop descriptor; TC-RING-002 ring full; TC-RING-003 ring empty; TC-RING-004 descriptor error stops chain. |
| 23 | Graph scheduler | TC-GRAPH-001 two-layer chain; TC-GRAPH-002 three-layer chain; TC-GRAPH-003 dependency not ready stalls; TC-GRAPH-004 error recovery. |
| 24 | Split and concat tensor movement | TC-SPLIT-001 channel split; TC-CONCAT-001 channel concat; TC-MOVE-001 no data corruption; TC-MOVE-002 partial channels. |
| 25 | Upsample and C2f sequencing | TC-UP-001 2x nearest upsample; TC-C2F-001 small C2f-like chain; TC-C2F-002 tensor shape propagation. |
| 26 | Maxpool and SPPF | TC-POOL-001 2x2 maxpool; TC-POOL-002 5x5 or selected SPPF pool; TC-SPPF-001 repeated maxpool chain; TC-SPPF-002 concat compatibility. |
| 27 | LUT-SiLU activation | TC-SILU-001 LUT correctness; TC-SILU-002 monotonic/edge values; TC-SILU-003 error bound vs Python model; TC-ACT-003 mode routing. |
| 28 | Detect-head convolution and raw tensor output | TC-DETECT-001 detect-head-like conv; TC-RAW-001 tensor shape/layout; TC-RAW-002 byte-exact export; TC-HOST-001 host can parse raw tensor. |
| 29 | Host software integration and demo path | TC-HOST-002 descriptor write/read; TC-HOST-003 CPU vs IP tensor compare; TC-HOST-004 decode/NMS compatibility; DEMO-001 end-to-end script dry run. |
| 30 | Performance evaluation and full system regression | REG-SYS-001 all implemented targets; PERF-001 kernel speedup; PERF-002 full-system overhead; PERF-003 counters sanity. |

| Week | Focus | Key tests / evidence |
| --- | --- | --- |
| 31 | Final documentation and evidence package | DOC-001 claim/evidence mapping; DOC-002 no-go claim audit; QA review of diagrams and code references. |
| 32 | Final demo rehearsal and defense delivery | DEMO-002 live or recorded demo; DEF-001 Q&A checklist; REL-001 final repository/package freeze. |

# Appendix B - Weekly Review Template

| Review item | Question to answer |
| --- | --- |
| Scope | Did this week's work remain within the planned primary target and avoid unreviewed scope creep? |
| RTL status | Which modules compiled, simulated and passed directed tests? |
| Verification status | Which TC IDs passed, failed or were not run? |
| Golden model | Was the Python/C++ reference updated and checked against known cases? |
| Waveforms | Which timing-sensitive waveforms were reviewed and saved? |
| Host contract | Did any register, descriptor, tensor layout or byte ordering contract change? |
| Performance | Were counters or timing logs collected? Were kernel and system metrics separated? |
| Risks | Which risks increased or decreased? Is a mitigation needed before next week? |
| Gate | Is the exit gate passed, waived with issue ID, or failed? |

# Appendix C - Final Submission Checklist

Architecture specification matches the implemented feature status.

RTL implementation guide matches actual module names and interfaces.

32-week plan final status table marks every primary target as implemented, partial, disabled or host-side.

All final claims map to logs, waveforms or demo screenshots.

CPU-only vs CPU+IP comparison includes both kernel and full-system timing.

Final slides include host/software partition and non-claim disclaimer.

No diagram implies that the FPGA alone performs full image-to-box YOLOv8n execution unless that is actually true.